## Sheet1
| Comments | Comments | % comp
Overall Status | Overall testing shows strong coverage and a high pass rate, with no major blockers identified, keeping the project on track for release. | 1 | 40
E2E | The End-to-End (E2E) testing has been largely successful, with all critical business workflows validated and only a few minor defects remaining. | 2 | 30
UAT | ser Acceptance Testing (UAT) has been completed with stakeholder sign-off, and feedback has been positive, suggesting minor enhancements for future iterations. | 3 | 70
NFT | Non-Functional Testing (NFT) is progressing steadily, with performance and security assessments underway; early results indicate acceptable system behavior under load, though a couple of medium-level vulnerabilities are being addressed. | 1 | 20

## Sheet2
Testing Phase | Total test planned | Completed | Planned % | % Completion
E2E | 240 | 120 | 50 | 50
NFT | 120 | 12 | 10 | 10
Regression 1 | 23 | 12 | 52.1739 | 52.1739
Regression 2 | 300 | 35 | 11.6667 | 11.6667
Regression 3 | 490 | 400 | 81.6327 | 81.6327
UAT | 10 | 5 | 50 | 50

## Sheet3
Date | Planned | Actual | Date | Planned | Actual
2025-09-14 | 100 | 100 | 2025-09-14 | 100 | 100
2025-09-15 | 93 | 98 | 2025-09-15 | 93 | 90
2025-09-16 | 86 | 97 | 2025-09-16 | 86 | 87
2025-09-17 | 79 | 82 | 2025-09-17 | 79 | 70
2025-09-18 | 72 | 80 | 2025-09-18 | 72 | 67
2025-09-19 | 65 | 80 | 2025-09-19 | 65 | 55
2025-09-20 | 58 | 80 | 2025-09-20 | 58 | 45
2025-09-21 | 51 | 80 | 2025-09-21 | 51 | 40
2025-09-22 | 44 | 50 | 2025-09-22 | 44 | 30
2025-09-23 | 37 | 50 | 2025-09-23 | 37 | 25
2025-09-24 | 30 | 50 | 2025-09-24 | 30 | 25
2025-09-25 | 23 | 50 | 2025-09-25 | 23 | 18
2025-09-26 | 16 | 20 | 2025-09-26 | 16 | 10
2025-09-27 | 0 | 20 | 2025-09-27 | 0 | 10

## Sheet4
Component | Test Status | Sign of Status | Commentry
Item 1 | Completed | Signed off
Item 2 | Completed | Signed off
Item 3 | Completed | Signed off
Item 4 | Completed | Signed off
Item 5 | Completed | In Progress | Delayed due to evidence review
Item 6 | Completed | In Progress | Delayed due to evidence review
Item 7 | Completed | In Progress
Item 8 | Completed | In Progress
Item 9 | Completed | Blocked
Item 10 | Completed | Signed off
Item 11 | Completed | Signed off

## Sheet 5
Defect ID | Status | Severity | Applications | Summary
1234 | Open | Critical | App1 | Overall testing shows strong coverage and a high pass rate, with no major blockers identified, keeping the project on track for release.
1234 | In Development | Critical | App2 | Overall testing shows strong coverage and a high pass rate, with no major blockers identified, keeping the project on track for release.
1234 | In Development | Critical | App2 | Overall testing shows strong coverage and a high pass rate, with no major blockers identified, keeping the project on track for release.
1234 | In Development | Critical | App2 | Overall testing shows strong coverage and a high pass rate, with no major blockers identified, keeping the project on track for release.
1234 | In Development | Significant | App4 | Overall testing shows strong coverage and a high pass rate, with no major blockers identified, keeping the project on track for release.
1234 | In UAT | Significant | App4 | Overall testing shows strong coverage and a high pass rate, with no major blockers identified, keeping the project on track for release.
1234 | In E2E | Medium | App7 | Overall testing shows strong coverage and a high pass rate, with no major blockers identified, keeping the project on track for release.
1234 | In E2E | Medium | App8 | Overall testing shows strong coverage and a high pass rate, with no major blockers identified, keeping the project on track for release.

## Sheet6
Open | 20 | App1 | 25
Closed | 5 | App2 | 8
Developed | 4 | App3 | 5
Reopened | 3 | App4 | 3
In UAT | 1 | App5 | 2
In End UAT | 4 | App6 | 5